UNIT2 MINI PROJECT

Enterprise Student Record and Academic Management Platform

Agile Project Planning and Scrum Implementation

Student Name: Jayesh Somavanshi

PRN: 2125UDSM1090

Branch: CSE-AIDS

1. Agile Project Planning Report

1.1 Introduction

This report converts the Unit1 product discovery work for the Enterprise Student Record and Academic Management Platform into an Agile delivery plan. Scrum is used because the platform can be delivered in short, reviewable increments while students, faculty members, administrators and examination staff provide continuous feedback.

1.2 Agile Approach

The work is organized as a prioritized Product Backlog. The Scrum Team selects the highest-value ready stories for two-week sprints, produces a potentially usable increment, reviews it with stakeholders and improves its working method in a retrospective. Changes are managed by refining and re-prioritizing the backlog rather than interrupting active sprint work.

1.3 Definition of Done

Acceptance criteria are satisfied and demonstrated.

Code or prototype is reviewed and linked to the relevant story.

Required validations, role permissions and error messages are checked.

Data changes are documented and test data is protected.

The Product Owner accepts the story in the Sprint Review.

2. Product Vision and Scrum Team Structure

2.1 Product Vision

To incrementally deliver a secure, easy-to-use academic platform that gives students, faculty and institutional staff one reliable place to manage student records, course registration, attendance, examinations, results and academic reports.

2.2 Scrum Team Structure and Roles

| Role | Member / Representative | Responsibility |
| --- | --- | --- |
| Product Owner | Academic Administrator / Dr. Mehta | Owns product value, clarifies needs, accepts completed stories and prioritizes the backlog. |
| Scrum Master | Project Coordinator | Facilitates Scrum events, removes impediments and protects the team from unplanned work. |
| Development Team | Developer, UX designer, QA engineer, database support | Designs, builds, tests and documents each sprint increment. |
| Stakeholders | Students, Faculty, Examination Cell, IT Support | Provide feedback in reviews and confirm the solution meets academic workflows. |

2.3 Scrum Events and Artefacts

| Item | Cadence / Owner | Purpose |
| --- | --- | --- |
| Sprint Planning | Start of every two-week sprint; Scrum Team | Set Sprint Goal, select stories and create the Sprint Backlog. |
| Daily Scrum | 15 minutes each working day; Development Team | Inspect progress, coordinate work and identify impediments. |
| Sprint Review | End of sprint; Product Owner and stakeholders | Demonstrate the increment and adapt the Product Backlog. |
| Sprint Retrospective | After review; Scrum Team | Identify improvements to quality, collaboration and delivery. |
| Product Backlog / Sprint Backlog | Product Owner / Development Team | Maintain ordered future work and the selected current-sprint plan. |

3. Epics and User Stories

3.1 Epic Documentation

| Epic ID | Epic | Business Value | Release |
| --- | --- | --- | --- |
| E1 | Identity and Student Profiles | Provides secure, accurate student records and role-based entry to the platform. | Release 1 |
| E2 | Course Registration | Enables students to view available courses and submit valid registrations. | Release 1 |
| E3 | Attendance Management | Lets faculty record attendance and students monitor eligibility. | Release 1 |
| E4 | Examinations and Results | Supports controlled result entry, publication and student viewing. | Release 2 |
| E5 | Academic Reports | Gives administrators reliable reports for decisions and compliance. | Release 2 |

3.2 User Stories and Acceptance Criteria

| ID | User Story | Acceptance Criteria | SP |
| --- | --- | --- | --- |
| US-01 | As an administrator, I want to create a student record so that academic data starts from one trusted profile. | Mandatory PRN is unique; name, branch and contact are validated; authorized users can save and view the profile. | 5 |
| US-02 | As a student, I want to sign in and view my profile so that I can verify my academic information. | Valid credentials open the student dashboard; a student can view only own data; invalid login shows a clear message. | 5 |
| US-03 | As a student, I want to register for available courses so that my semester enrolment is recorded. | Only active courses are displayed; duplicate selection is prevented; a confirmation is shown after submission. | 8 |
| US-04 | As a faculty member, I want to record attendance by course and date so that attendance is accurate. | Faculty selects assigned course; each enrolled student is marked; saved attendance can be retrieved and corrected by an authorized user. | 8 |
| US-05 | As a student, I want to see my attendance percentage so that I can take action before shortages occur. | Percentage is calculated from recorded sessions; course-wise view is available; missing data is clearly indicated. | 5 |
| US-06 | As examination staff, I want to enter and validate results so that published marks are reliable. | Only authorized staff can edit results; marks are range-validated; status remains draft until approved. | 8 |
| US-07 | As a student, I want to view published results so that I know my academic performance. | Only approved results are visible; student sees own subjects and grades; unpublished data is not exposed. | 5 |
| US-08 | As an administrator, I want to generate an academic report so that I can review records efficiently. | Report filters by student/course/semester; authorized users can export; generated data matches stored records. | 8 |
| US-09 | As IT support, I want role-based access so that confidential academic data is protected. | Roles restrict screens and actions; unauthorized requests are rejected; access changes are auditable. | 8 |
| US-10 | As an authorized user, I want to search student records so that I can retrieve information quickly. | Search supports PRN and name; only permitted records appear; empty results give useful feedback. | 5 |

4. Prioritized Product Backlog and Estimation

4.1 Prioritized Product Backlog

| Rank | Backlog Item | Priority | Reason | SP |
| --- | --- | --- | --- | --- |
| 1 | US-01 Student record creation | Must | Foundation for all academic modules. | 5 |
| 2 | US-02 Student sign-in and profile view | Must | Provides secure user access and early value. | 5 |
| 3 | US-09 Role-based access | Must | Protects confidential data across all modules. | 8 |
| 4 | US-03 Course registration | Must | Core semester workflow for students and staff. | 8 |
| 5 | US-04 Faculty attendance entry | Must | Addresses a high-frequency academic process. | 8 |
| 6 | US-05 Student attendance view | Should | Makes attendance information transparent. | 5 |
| 7 | US-06 Result entry and approval | Should | Enables reliable examination processing. | 8 |
| 8 | US-07 Student result view | Should | Delivers direct student value after approval. | 5 |
| 9 | US-10 Student search | Could | Improves staff efficiency after core data is available. | 5 |
| 10 | US-08 Academic reports | Could | Adds management insight after data modules stabilize. | 8 |

4.2 Story Point Estimation

Relative estimation uses the Fibonacci scale 1, 2, 3, 5, 8 and 13. Points represent combined effort, uncertainty and complexity, not calendar hours. The team uses planning poker and compares each story with the baseline student-profile story (5 points). Stories larger than 13 points must be split before selection.

| Points | Interpretation | Example |
| --- | --- | --- |
| 12 | Small, well understood change | Display a dashboard message. |
| 35 | Moderate workflow with limited dependencies | Student profile view or attendance percentage. |
| 8 | Complex workflow, validation and permissions | Course registration or result entry. |
| 13 | Too large for one sprint; split | Full report suite with several export formats. |

5. Sprint Planning and Sprint Backlogs

5.1 Release Assumptions

Each sprint is two weeks. The teams initial sustainable velocity is estimated at 20 story points per sprint. Release 1 targets a secure student-record, profile, course-registration and attendance foundation; Release 2 completes examinations, results, search and reporting.

5.2 Sprint 1  Foundation and Access

Sprint Goal: Establish secure access and a reliable student record so the platform has a usable foundation.

| Story / Task | Owner | SP | Planned Outcome |
| --- | --- | --- | --- |
| US-01 Student record creation | Developer + QA | 5 | Validated create/view student profile. |
| US-02 Student sign-in and profile view | Developer + UX | 5 | Student dashboard with own profile. |
| US-09 Role-based access (initial roles) | Developer + IT support | 8 | Student, faculty and administrator permissions. |
| Setup test data, review and documentation | Whole team | 2 | Demonstrable increment and evidence. |

5.3 Sprint 2  Registration and Attendance

Sprint Goal: Enable the core student enrolment and attendance workflow for one semester.

| Story / Task | Owner | SP | Planned Outcome |
| --- | --- | --- | --- |
| US-03 Course registration | Developer + UX | 8 | Available-course selection and confirmation. |
| US-04 Faculty attendance entry | Developer + QA | 8 | Course/date attendance recording. |
| US-05 Student attendance view | Developer | 5 | Course-wise percentage display. |
| Sprint test and stakeholder demonstration | Whole team | 2 | Validated end-to-end workflow. |

5.4 Sprint 3  Results and Insight

Sprint Goal: Provide controlled result handling and useful academic retrieval for authorised users.

| Story / Task | Owner | SP | Planned Outcome |
| --- | --- | --- | --- |
| US-06 Result entry and approval | Developer + Examination representative | 8 | Draft, validation and approval workflow. |
| US-07 Student result view | Developer + QA | 5 | Published results visible to the right student. |
| US-10 Student search | Developer | 5 | Permission-aware search by PRN or name. |
| Review, regression test and documentation | Whole team | 2 | Accepted increment ready for release. |

6. Scrum Board and Burndown Chart

6.1 Sprint 2 Scrum Board Snapshot

| To Do | In Progress | Testing / Review | Done |
| --- | --- | --- | --- |
| Attendance percentage display (US-05) | Attendance entry screen and validation (US-04) | Course-registration confirmation (US-03) | Course catalogue and enrolment validation (US-03) |
| Accessibility checks and help text | Role permission checks | Attendance retrieval test cases | Sprint planning and test data setup |

6.2 Sprint 2 Burndown Chart Data

The sprint begins with 23 story points. The remaining-work values are reviewed each day in the Daily Scrum; a rising or flat line triggers discussion about blockers, scope and the plan to meet the Sprint Goal.

| Day | Ideal Remaining SP | Actual Remaining SP | Interpretation |
| --- | --- | --- | --- |
| 0 | 23 | 23 | Sprint commitment confirmed. |
| 1 | 21 | 23 | Environment setup and story clarification. |
| 2 | 18 | 20 | Registration implementation begins. |
| 3 | 16 | 18 | Validation work in progress. |
| 4 | 13 | 15 | Attendance screen started. |
| 5 | 11 | 13 | Mid-sprint review identifies test cases. |
| 6 | 8 | 10 | Attendance save function completed. |
| 7 | 6 | 7 | Student view in testing. |
| 8 | 3 | 4 | Defects resolved and demonstration prepared. |
| 9 | 0 | 0 | All committed work accepted. |

6.3 Burndown Visual

Day:          0     1     2     3     4     5     6     7     8     9

Actual SP:   23    23    20    18    15    13    10     7     4     0

Trend:

7. Sprint Review and Sprint Retrospective

7.1 Sprint Review

At the Sprint 2 review, the team demonstrates course registration, faculty attendance entry and student attendance viewing with representative student and course data. The Product Owner checks the agreed acceptance criteria. Faculty stakeholders request a quick filter for absent students; this is recorded as a new backlog item rather than added to the completed sprint.

| Review Input | Decision |
| --- | --- |
| US-03 Course registration | Accepted: course visibility, duplicate prevention and confirmation operate as expected. |
| US-04 Attendance entry | Accepted: faculty can record, save and retrieve attendance for an assigned course. |
| US-05 Attendance view | Accepted: students see course-wise percentage and clear missing-data messages. |
| New stakeholder feedback | Add absent student filter to Product Backlog and estimate in refinement. |

7.2 Sprint Retrospective

| What Went Well | What to Improve | Action for Next Sprint |
| --- | --- | --- |
| Early acceptance-criteria discussion reduced rework. | Test cases were prepared late for the attendance module. | QA pairs with developer while each story is in progress. |
| Daily Scrum exposed a role-permission blocker quickly. | Course data was not ready on the first day. | Prepare anonymized seed data before Sprint Planning ends. |
| Stakeholder demo used realistic academic workflow. | Some tasks were too broad for visible progress tracking. | Break stories into smaller board tasks with owners. |

8. Agile Framework Comparison

| Framework | Strength | Limitation | Suitability for This Project |
| --- | --- | --- | --- |
| Scrum | Timeboxed sprints, clear roles and frequent reviews make incremental academic workflows visible. | Requires disciplined backlog refinement and stakeholder availability. | Selected: the project has a defined product vision and benefits from two-week demonstrations. |
| Kanban | Continuous flow and visible work-in-progress limits suit support and maintenance work. | Does not prescribe sprint goals or formal planning events. | Useful later for IT support, defects and operational enhancements. |
| Extreme Programming (XP) | Strong engineering practices such as pairing, automated testing and continuous integration improve quality. | Requires high technical discipline and close developer collaboration. | Can complement Scrum for code quality and frequent testing. |
| Waterfall | Clear sequential documentation can suit stable, regulated work. | Late feedback makes changing academic requirements expensive. | Not selected for primary delivery because user feedback is needed early and often. |

9. Timeline and Release Roadmap

| Period | Sprint / Phase | Key Deliverables | Release Outcome |
| --- | --- | --- | --- |
| Weeks 12 | Sprint 1 | Student record, profile view, initial roles and access controls. | Secure foundation demonstrated. |
| Weeks 34 | Sprint 2 | Course registration, faculty attendance entry, student attendance view. | Release 1: Core Academic Operations. |
| Weeks 56 | Sprint 3 | Result entry, approval, result view and student search. | Examination workflow demonstrated. |
| Weeks 78 | Sprint 4 | Academic reports, export, feedback fixes and release hardening. | Release 2: Academic Insight and Reporting. |
| After Release 2 | Continuous improvement | Performance, audit improvements, integrations and support requests. | Roadmap refined from actual stakeholder feedback. |

9.1 Release Roadmap Flow

DISCOVERY  SPRINT 1: FOUNDATION  SPRINT 2: CORE OPERATIONS  RELEASE 1  SPRINT 3: RESULTS  SPRINT 4: REPORTS  RELEASE 2  IMPROVEMENT

10. Conclusion

The Unit2 Agile Mini-Project provides a practical Scrum plan for delivering the Enterprise Student Record and Academic Management Platform. It translates the Unit1 vision, requirements and stakeholder needs into epics, clear user stories, measurable acceptance criteria, a prioritized backlog, relative estimates and achievable sprint goals. Regular reviews ensure that students, faculty, administrators and examination staff can inspect each increment, while retrospectives strengthen the teams delivery process. The roadmap therefore creates a controlled but adaptable path from product discovery to a usable academic platform.